## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name | Group 7 |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Crystal | Delia | Nora | Vera
Project Start Date: | 14/09/2021 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-10 to 2022-01-04
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-10 to 2022-01-04
Interation 01
Interation planning | Goal | Delia | 45% | 2021-10-10 | 1
stakerholder register | High Risk | All numbers | 100% | 2021-10-11 | 3
persona | Low Risk | Nora | 50% | 2021-10-16 | 10
user testing | Milestone | Crystal | 60% | 2021-10-30 | 1
review | Med Risk | Vera | 40% | 2021-10-16 | 6
Interation 02
Gantt chart | High Risk | All numbers | 60% | 2021-11-10 | 6
GitHub boards | On Track | All numbers | 50% | 2021-11-08 | 5
Test new changes | Low Risk | All numbers | 33% | 2021-11-13 | 11
review | Milestone | All numbers | 30% | 2021-11-15 | 1 | bar: 2021-11-15
Interation 03
Risk register | On Track | All numbers | 40% | 2021-10-25 | 4
Meeting | Med Risk | All numbers | 50% | 2021-10-28 | 14
Website intergration & pubilc | On Track | All numbers | 60% | 2021-11-12 | 6
user testing | Goal | All numbers | 30% | 2021-12-07 | 3 | 2021-12-07: 2; 2021-12-08: 2; 2021-12-09: 2
review | Low Risk | All numbers | 35% | 2021-10-16 | 19
To add more data, Insert new rows ABOVE this one
Formulas:
Vera = [Vera, row above]-2
Vera = [Vera, row above]+5

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-10 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2021-11-11 to 2022-01-05
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-10 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2021-11-15 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2021-11-07 | 10
Task 4 | Milestone |  |  | 2021-11-30 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-11-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-16 | 13
Task 2 | On Track |  | 50% | 2021-11-18 | 9
Task 3 | Low Risk |  | 33% | 2021-11-23 | 11
Task 4 | Milestone |  |  | 2021-11-25 | 1 | bar: T
Task 5 |  |  |  | 2021-11-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-25 | 4
Task 2 | Med Risk |  |  | 2021-11-28 | 14
Task 3 | On Track |  |  | 2021-12-13 | 6
Task 4 | Goal |  |  | 2021-12-17 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2021-11-16 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-20 | 15
Task 2 |  |  |  | 2022-01-03 | 5
Task 3 | Milestone |  |  | 2022-02-14 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-10 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-15 to 2022-01-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-15 to 2022-01-09
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-10 | 3
Task 2 | Milestone |  |  | 2021-11-15 | 1 | bar: 2021-11-15
Task 3 | Low Risk |  | 50% | 2021-11-07 | 10
Task 4 | Milestone |  |  | 2021-11-30 | 1 | bar: 2021-11-30
Task 5 | Med Risk |  | 10% | 2021-11-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-16 | 13
Task 2 | On Track |  | 50% | 2021-11-18 | 9
Task 3 | Low Risk |  | 33% | 2021-11-23 | 11
Task 4 | Milestone |  |  | 2021-11-25 | 1 | bar: 2021-11-25
Task 5 |  |  |  | 2021-11-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-25 | 4
Task 2 | Med Risk |  |  | 2021-11-28 | 14
Task 3 | On Track |  |  | 2021-12-13 | 6
Task 4 | Goal |  |  | 2021-12-17 | 3 | 2021-12-17: 2; 2021-12-18: 2; 2021-12-19: 2
Task 5 | Low Risk |  |  | 2021-11-16 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-20 | 15
Task 2 |  |  |  | 2022-01-03 | 5
Task 3 | Milestone |  |  | 2022-02-14 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one